Kindred Care — ACU weekly

Project Oversight Team 9:30–10:00  ·  Workshop 1.2.B 10:00–10:30

Brad · Russell Carrington · Bill Russell · Lois McKellar  ·  Microsoft Teams

If only three things land: dated positions on the two 61-day blockers, and Lois starting the ethics pathway.

Weekly

9:30 – 10:00

1.  Housekeeping   2 min

Russell is on leave Thu 3, Fri 4 and Mon 7 September — which covers his own 1.2.R&D workshop tomorrow.

Does it move, or does someone else run it? Settle it here, not by email.

2.  Since last week   5 min — report, don't dwell

Four dormant relationships revived, all with ACU visible:

- SCHHS Maternity — invitation to present to Maternity Leadership accepted; Jo coordinating a date. Grant failure disclosed up front.

- Wishlist — Brendan Hogan phoned; meeting confirmed 2pm next week at Birtinya. This is the pilot's funding leg.

- Victoria — Fiona contacted; raising it with Jenny Dempster (Gippsland Southern) directly. First Victorian movement in four months.

- Sequence set: Wishlist → SCHHS maternity → combine if interest holds on both sides.

Also: unit cost resolved, COI register stood up, Ged's introductions formally declared.

3.  The two blockers   10 min — this is the meeting's job

Both 61 days open. Both ACU-side. Both gate UCAC on 16 October.

- ACU's $650,000 — no identified source

- Heads of Agreement and IP audit — we are holding all ownership language until ACU's draft lands

Ask for dated positions, not status. “When will we know?” rather than “Where is it up to?” If a date cannot be given, that is itself the answer and we plan around it.

4.  Lois — three asks   8 min

Ethics pathway for a 150-mother pilot — route and realistic duration. The one item between here and evidence that cannot be compressed. Start it this week.

ACM. The relationship is warm — Kelley Lennon (their Chief Midwife) and Gabby Earls met me in April and offered an advisory board and short courses. It has gone stale on our side. I'd like to route the re-approach through you.

Clinical review of the AI impact assessment before it goes anywhere external.

5.  Marie   3 min

Outcome of Monday, and the next step. A scope conversation, not a title conversation.

6.  Two flags   2 min

- Build completes mid-to-late September — before UCAC. That changes what we can show.

- Content Advisory Panel has slipped since 14 Aug. Wallace, Simpson and Byatt nominated 12 Aug.

Workshop 1.2.B — Business

10:00 – 10:30

1.  Pricing   15 min

Position resolved: the Pricing Model's $28k / $48k / $72k / $95k is canonical, banded by births per year with included-mother caps. Adding an $18,000 entry tier for 150 mothers as the pilot on-ramp. Enterprise needs an inclusion cap — it runs at 6% margin, and negative once platform support is loaded.

Ask: endorsement to make this the single schedule and retire the Business Plan's list.

2.  Which budget does a health service buy this from?   15 min

The question everything commercial sits downstream of, and we have not answered it. No Australian health service holds a patient-education budget line. Workforce capacity and equity of access do have lines — and they are the Taskforce's own priorities.

Ask: ACU's read on where this actually gets paid from — and whether regional Victorian services can contract as a network rather than individually. Thirty-three of fifty-two providers turn on that answer.

Actionable tasks out of the meeting

| # | Task | Owner | By |
| --- | --- | --- | --- |
| 1 | Thursday 1.2.R&D — move it or nominate cover | Russell | TODAY |
| 2 | Dated position on ACU's $650,000 | Russell + Bill | AT MEETING |
| 3 | Dated position on the Heads of Agreement | Russell | AT MEETING |
| 4 | Ethics pathway — route and realistic duration | Lois | THIS WEEK |
| 5 | ACM re-approach routed through Lois | Lois + Brad | This week |
| 6 | Clinical review of the AI impact assessment | Lois | Before external use |
| 7 | Endorse the canonical pricing schedule | Russell + Bill | At meeting |
| 8 | Can regional Victorian services contract as a network? | Lois | Next weekly |
| 9 | Content Advisory Panel — charter and roster | Lois | Next weekly |
| 10 | Sunshine Coast POC endorsement | Russell | This week |

Hold back today

The D-23 sovereignty question and the evals sequencing both belong in tomorrow's R&D workshop — assuming it runs. The Ged / Victorian channel correction is a Russell one-to-one, not a group item.