Workshop 1.2.B — Business

Kindred Care  ·  Wednesday 10:00–10:30  ·  immediately following the weekly

Brad · Russell Carrington · Bill Russell · Lois McKellar

What this workshop is for

Russell's brief for the 1.2 series is to identify the streams needing coverage for a complete profile, feeding Enterprise Commercialisation Plan generation — and to set up the larger workshops that follow. It is a scoping session, not a decision session.

So the output today is a stream map with owners, not resolved content. Thirty minutes will not settle pricing and the buyer question and the plan structure. It will comfortably agree the streams and land the one that matters most.

1.  Proposed stream map   12 min — the main event

Ten streams for a complete commercial profile. Status is mine and open to challenge; the point is to agree the list and the owners.

| # | Stream | What it covers | Status | Owner |
| --- | --- | --- | --- | --- |
| 1 | Market and demand | Pull is real at every level of the profession; evidence of use is not | STRONG | Brad |
| 2 | Positioning and category | Workforce and equity, never patient education — this sets the price ceiling | DECIDED | Brad |
| 3 | Pricing and unit economics | Schedule canonical; unit cost resolved; Enterprise tier needs an inclusion cap | READY | Brad + Hector |
| 4 | Route to market | Who introduces, who buys, and through which procurement pathway | GAP | Brad + Lois |
| 5 | Revenue model and forecast | Two priced streams sit outside the forecast; no downside case is carried | GAP | Brad + CFO |
| 6 | Funding and capital | BVUIP structure confirmed; ACU's $650k source open 61 days | BLOCKED | Russell + Bill |
| 7 | Entity, ownership, IP terms | Holding line until ACU's Heads of Agreement lands | BLOCKED | Russell |
| 8 | Partnerships and channel | ACM warm; two chief midwives engaged; foundation conversation live | MOVING | Brad + Lois |
| 9 | Procurement and assurance | VPDSS, ISO 27001/42001, data residency — commercial gates, not IT items | SCOPED | Brad |
| 10 | Team and capability | Throughput is the constraint; Marie's scope is the fix | OPEN | Brad + Lois |

Four are strong, three are gaps, two are blocked on ACU, one is open. The two blocked ones are the same two blockers from the weekly — they are not only governance items, they are commercial streams that cannot be written.

2.  The gap that matters most   10 min

Which budget does a health service actually buy this from?

There is no patient-education budget line in an Australian public health service. If a CFO files us there, we are compared to free pregnancy apps and cut in the first tight year. Workforce capacity and equity of access do have budget lines — and they are the Maternity Taskforce's own words. So this is not a messaging choice. It sets our price ceiling.

What I want from ACU: your read on where this gets paid from, and who actually signs.

And the question underneath it, for Lois: can regional Victorian services contract as a network rather than one at a time? Thirty-three of Victoria's fifty-two providers are regional and small. Our fixed cost per site is high enough that serving them individually is hard at any price they would accept. If they can buy as a group, regional opens. If they cannot, the model needs rethinking.

3.  Pricing — endorsement, not debate   5 min

Position resolved and circulated: $28k / $48k / $72k / $95k, banded by births per year with included-mother caps. New $18,000 entry tier at 150 mothers as the pilot on-ramp. Enterprise runs at 6% gross margin and negative once platform support is loaded — it needs an inclusion cap with per-mother overage.

Ask: endorsement to make this the single schedule and retire the Business Plan's list. If there is disagreement, take it offline rather than spend the workshop on it.

4.  Close   3 min

- Agree the stream list and the owners

- Agree which streams the larger follow-on workshops cover first

- Confirm what feeds the 16 Sept Steering Committee

Talking points worth having ready

On demand — the reframe that changes the read:

We have pull at every level of the profession — a national college, two chief midwives, a health service's maternity leadership, a health foundation, four regional services. What we have not had is the capacity to convert it. That is a throughput story, not a demand story.

On route to market — say it plainly, it is the business of this workshop:

ACU gives us academic credibility and national access to the profession. Victorian service relationships are coming from elsewhere. The plan should say that rather than claim a channel we do not have — it is stronger written accurately.

On what we are actually asking investment for:

The build lands before UCAC. So we are not asking anyone to fund a product. We are asking them to fund the evidence that it works and the capacity to convert demand we can already demonstrate.

Hold back

D-23 and the evals sequencing are R&D workshop items. The Ged channel detail is a Russell one-to-one — in this room, keep route-to-market at the level of the stream, not the individual introductions.